## Overview
PayPal Payments Integration - Setup & Cost Guide
DriveDeal premium subscriptions (US customers only) ¦ Prepared 13 Oct 2026 ¦ Fee data: PayPal US Merchant Fees, updated 1 Oct 2026
Purpose
DriveDeal will collect yearly premium subscription payments (Dealer $500/year, Buyer $100/year) through PayPal. This workbook lists what is needed to open and activate the PayPal Business account and why, which payment methods customers can use, the full PayPal cost breakdown, the main financial risks, and the steps to go live.
Key points
No Stripe needed | PayPal alone accepts PayPal wallet, credit cards and debit cards (Visa, Mastercard, Amex, Discover) for US customers.
No fixed costs | Business account, developer access, testing, API use and the custom card form have no monthly or setup fee. PayPal charges only a % + fixed fee per successful payment.
Custom checkout | With PayPal's Advanced Credit & Debit Card Payments, the card form is built into DriveDeal's own pages and branding. The PayPal wallet login itself stays on PayPal's screen.
Automatic renewal | The customer's payment method is saved securely by PayPal (Vault); DriveDeal charges it automatically each year. Card numbers never reach DriveDeal's servers.
Cash flow | New PayPal accounts typically have incoming payments held for up to 21 days. Customers still get premium immediately; only DriveDeal's withdrawal is delayed.
Main risks | Customer disputes/chargebacks, fees not returned on refunds, and payment holds/reserves on a new account. See 'Risks & Mitigation'.
Headline numbers (linked from 'Cost per Plan')
Dealer plan - DriveDeal receives (custom card form) | 485.26
Dealer plan - DriveDeal receives (PayPal wallet) | 482.06
Buyer plan - DriveDeal receives (custom card form) | 96.82
Buyer plan - DriveDeal receives (PayPal wallet) | 96.02
Sheets in this workbook
Account Setup Checklist | Every detail/document needed to open and activate the account, why PayPal needs it, who provides it, and a status column to track progress.
Payment Methods | How customers can pay and whether each method supports yearly auto-renewal.
PayPal Fee Schedule | Every PayPal US fee, one per line, and whether it applies to DriveDeal.
Cost per Plan | Fee and net amount for each plan and payment method, plus an editable example-year projection.
Sources | Where every fee and policy figure came from.
Legend
Blue text, yellow fill | Editable input - change it and the totals update.
Green text | Value linked from another sheet.
Status column | On 'Account Setup Checklist' and 'Timeline & Next Steps': choose Not started / In progress / Done / Not applicable.
Note | Fees are PayPal's published US rates as of 1 Oct 2026 and can change. Confirm the rates shown in DriveDeal's PayPal account after approval.

## Account Setup Checklist
Account Setup Checklist
What is needed to open, verify and activate the PayPal Business account - and why
# | Item | Details / example | Why PayPal (or DriveDeal) needs it | Provided by | Required? | Needed by
A. Business information
1 | Legal business name | Exactly as registered with the state / IRS. | Identity and business verification (KYC). Also shown to customers on PayPal receipts. | Client | Mandatory | Account opening
2 | Business type | Sole proprietor, LLC, partnership or corporation. | Decides which verification documents PayPal asks for. | Client | Mandatory | Account opening
3 | EIN (Employer Identification Number) | 9-digit federal tax ID (IRS letter CP-575). Sole proprietors may use SSN. | Business verification and US tax reporting - PayPal issues Form 1099-K for payments received. | Client | Mandatory | Account opening
4 | Registered business address | US physical address (no PO box). | Verification and regulatory compliance. | Client | Mandatory | Account opening
5 | Business phone (mobile) | A mobile number that will be confirmed by SMS. | Security codes; PayPal's risk team contact. A confirmed mobile number is one of PayPal's conditions for releasing held funds faster. | Client | Mandatory | Account opening
6 | Business email (login) | Shared mailbox recommended, e.g. payments@<company domain>. | Account login and all payment, dispute and policy notices. A shared mailbox avoids missed dispute deadlines when staff change. | Client | Mandatory | Account opening
7 | Customer service email & phone | Support contact customers can reach. | Printed on customers' PayPal receipts. Customers who can reach DriveDeal easily are less likely to file disputes. | Client | Mandatory | Account opening
8 | Business category & description | e.g. 'Online vehicle marketplace - annual premium subscriptions for dealers and buyers'. | PayPal's risk assessment. A description that does not match what is sold triggers account reviews and holds. | Client | Mandatory | Account opening
9 | Expected sales volume | Estimated monthly sales and average payment size (e.g. $100 and $500). | Underwriting. Accurate estimates reduce the chance of reserves when sales grow. | Client | Mandatory | Account opening
10 | Website URL | Live HTTPS address of the DriveDeal application. | PayPal reviews the website, especially for the custom card form approval. | Client / Dev team | Mandatory | Card form approval
B. Owner identity (KYC)
11 | Primary owner - legal name, date of birth, home address | The person legally responsible for the account. | Required by US anti-money-laundering / Know-Your-Customer rules. | Client | Mandatory | Account opening
12 | Primary owner - SSN or ITIN | Social Security Number. | Identity verification. | Client | Mandatory | Account opening
13 | Beneficial owners (25%+ ownership) | Name, date of birth, address and SSN of each person owning 25% or more. | Required by US beneficial-ownership rules for companies. | Client | If applicable | Account opening
14 | Government photo ID | Driver's license or passport. | Requested if identity cannot be confirmed automatically. | Client | If requested | During verification
15 | Business registration documents | Articles of incorporation / organization, EIN letter. | Requested if business details cannot be confirmed automatically. | Client | If requested | During verification
C. Banking
16 | US business bank account | Bank name, routing number, account number. | Where DriveDeal's PayPal balance is withdrawn to (standard transfer is free). A confirmed bank is a condition for faster release of held funds. | Client | Mandatory | Before first withdrawal
17 | Bank confirmation (micro-deposits) | PayPal sends two small deposits; enter the amounts in PayPal. | Proves the account belongs to the business. Takes 1-3 business days. | Client | Mandatory | Before first withdrawal
D. Website pages (PayPal review)
18 | Terms of Service page | Rules for using DriveDeal premium. | Required by PayPal for approval; used as evidence in disputes. | Client (legal) / Dev team | Mandatory | Before go-live
19 | Privacy Policy page | How customer data is handled. | Required by PayPal and US privacy law. | Client (legal) / Dev team | Mandatory | Before go-live
20 | Refund & Cancellation Policy page | e.g. full refund within 14 days of a charge; cancelling stops the next renewal. | Required by PayPal. A clear policy reduces disputes. | Client (decision) / Dev team | Mandatory | Before go-live
21 | Pricing with auto-renewal disclosure | '$500/year, renews automatically on <date>, cancel anytime' + checkbox at checkout. | Several US states (e.g. California) require clear auto-renewal terms and reminders. Also the main evidence in renewal disputes. | Dev team | Mandatory | Before go-live
22 | Contact page | Support email, phone, business address. | Required by PayPal; reduces disputes. | Dev team | Mandatory | Before go-live
E. PayPal features to activate
23 | Advanced Credit & Debit Card Payments | Requested in PayPal developer dashboard (Live app). PayPal reviews the account; can take several days. | Lets customers enter card details on DriveDeal's own branded page, at a lower rate (2.89% + $0.29). | Client (account owner) | Recommended | Before go-live
24 | Vault (saved payment methods) | Enabled in the same app settings; may need PayPal approval in Live. | Required for automatic yearly renewal - the customer's card/PayPal is saved by PayPal and charged each year. | Client (account owner) | Mandatory | Before go-live
25 | Card statement name (soft descriptor) | e.g. 'DRIVEDEAL PREMIUM'. | What customers see on their card statement. A recognisable name prevents 'unrecognised charge' chargebacks. | Client / Dev team | Recommended | Before go-live
26 | Two-step login verification | Authenticator app or SMS on the PayPal login. | Protects the account and its funds. | Client | Recommended | Account opening
27 | Team user access | Separate PayPal logins with limited roles for staff/developers. | Avoids sharing the owner's password; access can be removed when people leave. | Client | Recommended | Before development
F. Technical items for the development team
28 | Developer dashboard access | developer.paypal.com - same login as the Business account. | Where API credentials and webhooks are created. | Client | Mandatory | Before development
29 | Sandbox Client ID & Secret | Test credentials - no real money. | Build and test the full payment flow safely. | Client / Dev team | Mandatory | Before development
30 | Live Client ID & Secret | Production credentials. | Real payments. Share through a secure channel only - never by email or chat. | Client | Mandatory | Go-live
31 | Webhook URL & Webhook ID | PayPal notification address on DriveDeal's server. | PayPal tells DriveDeal about renewals, refunds, failed payments and disputes automatically. | Dev team | Mandatory | Before development
32 | Plan prices confirmed | Dealer $500/year, Buyer $100/year, USD. | Configured in the application and charged on each renewal. | Client | Mandatory | Before development
33 | Refund policy decision | No refunds / refund within N days / prorated. | Implemented in the app and admin tools; drives refund and dispute cost. | Client | Mandatory | Before development

## Payment Methods
Payment Methods for Customers
All processed by PayPal - no Stripe or other processor required
Method | How the customer pays | Yearly auto-renewal? | PayPal fee % | Fixed fee | Recommendation
PayPal wallet | Clicks the PayPal button, logs into PayPal, pays with balance, bank or saved card. | Yes | 3.49% | 0.49 | Include - many customers prefer it.
Credit / debit card - custom card form | Enters card details directly on DriveDeal's branded checkout page (Advanced Credit & Debit Card Payments). No PayPal account needed. | Yes (with Vault) | 2.89% | 0.29 | Include - lowest fee and fully branded. Needs PayPal approval.
Credit / debit card - inside PayPal button | Clicks 'Debit or Credit Card' under the PayPal button and pays as a guest in PayPal's panel. | Yes | 2.99% | 0.49 | Fallback if custom card form approval is pending.

## PayPal Fee Schedule
PayPal US Fee Schedule
Source: PayPal US Merchant Fees, last updated 1 Oct 2026 (see Sources). Rates can change.
Category | Service / fee | Rate % | Fixed fee | Applies to DriveDeal? | Notes
Receiving payments
Receiving payments | PayPal Checkout (PayPal wallet) | 3.49% | 0.49 | Yes | Charged on every payment, including each yearly renewal.
Receiving payments | Advanced Credit & Debit Card Payments | 2.89% | 0.29 | Yes | Custom card form on DriveDeal's page. No monthly fee.
Receiving payments | Standard credit/debit card (in PayPal button) | 2.99% | 0.49 | Fallback | Guest card payment inside PayPal's button.
Surcharges
Surcharges | International transaction | 1.5% |  | Rarely | Added on top if the customer pays with a non-US card/account.
Surcharges | Currency conversion | 4% |  | No | 3-4% spread. Not charged when everything is in USD.
Disputes & refunds
Disputes & refunds | Dispute fee - standard (PayPal disputes) |  | 15 | Yes | Per dispute on PayPal-branded payments.
Disputes & refunds | Dispute fee - high volume |  | 30 | Risk | Applies if the account's dispute rate is high.
Disputes & refunds | Chargeback fee (card form payments) |  | 20 | Yes | Per chargeback filed through the customer's bank.
Disputes & refunds | Refund |  | 0 | Yes | Sending a refund is free, but the ORIGINAL fee is not returned.
Account & withdrawals
Account & withdrawals | Business account, developer account, sandbox |  | 0 | Yes | Free.
Account & withdrawals | API calls, webhooks, Vault, 3-D Secure |  | 0 | Yes | No separate fee listed - covered by the transaction fee.
Account & withdrawals | Monthly fee - Advanced Card Payments |  | 0 | Yes | No monthly fee.
Account & withdrawals | Standard transfer to bank (1-3 days) |  | 0 | Yes | Free.
Account & withdrawals | Instant transfer to bank | 1.5% |  | Optional | Minimum $0.50. Avoid by using standard transfer.
Account & withdrawals | Payments Pro (legacy) |  | 30 | No | Monthly. Not needed.
Account & withdrawals | Payflow Pro (legacy) |  | 25 | No | Monthly. Not needed.
Account & withdrawals | Invoicing subscription |  | 14.99 | No | Monthly. Not needed.

## Cost per Plan
Cost per Plan and Example Year
Blue/yellow cells are editable. All other numbers are formulas.
Inputs - plan prices (per year, USD)
Plan | Price
Dealer Premium | 500
Buyer Premium | 100
Fee and amount received per payment (fee rates are inputs - from PayPal Fee Schedule)
Plan / payment method | Price | Rate % | Fixed fee | PayPal fee | DriveDeal receives | Effective fee %
Dealer Premium
PayPal wallet | 500 | 3.49% | 0.49 | 17.94 | 482.06 | 3.588%
Card - inside PayPal button | 500 | 2.99% | 0.49 | 15.44 | 484.56 | 3.088%
Card - custom card form | 500 | 2.89% | 0.29 | 14.74 | 485.26 | 2.948%
Buyer Premium
PayPal wallet | 100 | 3.49% | 0.49 | 3.98 | 96.02 | 3.98%
Card - inside PayPal button | 100 | 2.99% | 0.49 | 3.48 | 96.52 | 3.48%
Card - custom card form | 100 | 2.89% | 0.29 | 3.18 | 96.82 | 3.18%
Note on B6: Source: DriveDeal pricing (backend settings DEALER_PREMIUM_PRICE).

## Risks & Mitigation (hidden)
Financial Risks & Mitigation
The three real risks of taking subscription payments through PayPal
Risk | What it is | Where it appears | Cost example | Likelihood | How DriveDeal reduces it
Dispute (PayPal) | Customer opens a complaint in PayPal (Activity > Report a problem), up to 180 days after payment. Disputed amount is frozen; DriveDeal has ~10 days to respond with evidence. If not settled, PayPal decides. | Email to DriveDeal; PayPal dashboard > Activity > Disputes; DriveDeal admin panel (via PayPal webhook - planned). | Lost $500 dealer dispute: $500 returned + $17.94 fee kept + $15 dispute fee = $532.94. | Medium | Renewal reminder emails 30 and 7 days before charging; one-click cancel; clear auto-renewal wording + consent checkbox; stored evidence (consent time, IP, usage, receipts); admin dispute alerts with deadline countdown; refund early rather than let a dispute escalate.
Chargeback (card) | Customer who paid by card asks their bank to reverse the charge (~120 days). The bank decides; PayPal forwards DriveDeal's evidence. | Email; PayPal dashboard > Disputes; DriveDeal admin panel (planned). | Lost $500 dealer chargeback: $500 + $14.74 fee kept + $20 chargeback fee = $534.74. | Medium | Same as above, plus a recognisable card-statement name (e.g. DRIVEDEAL PREMIUM) to prevent 'I don't recognise this charge'.
Seller Protection gap | PayPal Seller Protection mainly covers shipped physical goods. Online services/subscriptions are generally NOT covered. | - | Any lost dispute is absorbed by DriveDeal. | Certain | DriveDeal's own evidence and policies are the protection - see the measures above.
Refund fee not returned | When DriveDeal refunds a payment, PayPal keeps the original processing fee (even for partial refunds). | PayPal dashboard > Activity. | Refund of $500 PayPal-wallet payment: $17.94 lost. Refund of $100: $3.98 lost. | High | Publish a clear refund policy (recommended: full refund within 14 days of a charge). A quick refund (~$18) is far cheaper than a lost dispute (~$535).
New-seller payment hold | New accounts typically have incoming payments held up to 21 days before they can be withdrawn. Money is not lost - only delayed. | PayPal dashboard > Balance shows 'Pending / Payment on hold' with release date. | First weeks' revenue unavailable for up to 21 days. Customers are not affected - premium activates immediately. | High (first weeks) | Verify account fully before launch (EIN, ID, bank, mobile); mark held payments as delivered to speed release; request a monthly release limit; plan cash flow for the first month.
Rolling / fixed reserve | PayPal holds back part of sales (e.g. 10% for 90 days) if it sees higher risk: high-priced prepaid yearly service, sudden sales spikes, many disputes. | PayPal notification + dashboard > Balance. | 10% rolling reserve on $500: $450 available now, $50 after 90 days. | Low-Medium | Accurate business description and volume estimates; grow gradually; tell PayPal in advance about large launches; keep disputes under 1%.
Account limitation | PayPal restricts withdrawals (sometimes receiving) until documents are provided. | PayPal email + dashboard banner. | Funds frozen for days to weeks. | Low | Full verification up front; live website with Terms, Privacy, Refund and Contact pages; respond to PayPal requests the same day.
How a dispute progresses
1. Inquiry | Customer and DriveDeal message each other in PayPal's Resolution Center. About 20 days to settle (e.g. by refund).
2. Claim | If not settled, escalated to PayPal, which decides. DriveDeal submits evidence within ~10 days.
Chargeback | Separate path through the customer's bank. No negotiation with the customer; $20 fee applies.

## Timeline & Next Steps (hidden)
Timeline & Next Steps
Account approval runs in parallel with development in the PayPal test (sandbox) environment
# | Step | Owner | Estimated time | Depends on | Status
1 | Open PayPal Business account and complete verification (EIN, owner ID, address, mobile) | Client | 1-3 days | Checklist sections A-B | Not started
2 | Link and confirm US business bank account | Client | 1-3 business days | Step 1 | Not started
3 | Decide refund/cancellation policy and confirm plan prices | Client / Management | 1 week | - | Not started
4 | Share sandbox Client ID & Secret with development team (secure channel) | Client | Same day | Step 1 | Not started
5 | Build checkout, saved payment methods, renewals, webhooks, reminders, cancel button, dispute admin panel - test in sandbox | Dev team | To be estimated | Step 4 | Not started
6 | Publish Terms, Privacy, Refund and Contact pages; auto-renewal wording at checkout | Client (legal) / Dev team | 1-2 weeks | Step 3 | Not started
7 | Apply for Advanced Credit & Debit Card Payments and Vault in Live | Client | Several days (PayPal review) | Steps 1, 6 | Not started
8 | Set card statement name (e.g. DRIVEDEAL PREMIUM) | Client | Same day | Step 1 | Not started
9 | Create Live credentials, plans and webhook; switch application to live | Client / Dev team | 1 day | Steps 5, 7 | Not started
10 | Launch with gradual rollout; monitor holds, disputes and refunds | Client / Dev team | First 90 days | Step 9 | Not started

## Sources
Sources
Checked 13 Oct 2026
Source | Link
PayPal US Merchant Fees (official, last updated 1 Oct 2026) - all fee figures | https://www.paypal.com/us/webapps/mpp/merchant-fees
PayPal Business Fees (official) | https://www.paypal.com/us/business/paypal-business-fees
PayPal Help - New account payment holds (up to 21 days, release conditions) | https://www.paypal.com/us/cshelp/article/new-paypal-account-%E2%80%93-payments-on-hold-and-accessing-your-money-quicker-help848
NerdWallet - PayPal Fees 2026 | https://www.nerdwallet.com/article/small-business/paypal-fees
Chargeflow - PayPal chargebacks 2026 | https://www.chargeflow.io/chargebacks-101/paypal-chargeback
DriveDeal plan prices | DriveDeal application settings (Dealer $500/yr, Buyer $100/yr)